## Issues Report
Title | Description | Issue ID | URL | State | Assignee | Created At | Due Date | Milestone | Labels | Functions/Screens
Home screen | Link in the footer part is not working | 1 | Home screen (#10) · Issues · Group6 / Online-Learning · GitLab | Closed | DucNT | 2023-01-02 | 2023-03-02 | 1 | home | home
| The home page must display search menus, website logos, and courses included in the website | 2 |  | Closed | VinhTD | 2023-03-02
| Displays the course name, description and price of the course taken from the database | 3 |  | Closed | DungNTK | 410229
| Display the links at the footer of the page | 4 |  | Closed | KhangTD | 2023-04-03
| Display percentage of finish lesson out of total lesson for each course in home page | 5 |  | Closed | KienPT | 2023-04-03
| Image, logo, font, text, color should be display in acceptable size for better visual | 6 |  | Closed | KienPT | 2032-05-02
| Logo is haven't been changed yet | 7 | Logo page is missing (#22) · Issues · Group6 / Online-Learning · GitLab | Done | VinhTD | 20/02/2023 | 29/02/2023 | 2 | home | login
| Link in header part is not attached yet. Only "Learning" button is return to index page. | 8 | Header links (#15) · Issues · Group6 / Online-Learning · GitLab | Closed | KhangTD | 2023-10-02 | 2023-12-02 | 2 | home | home
| Percentage of finished lessons in course is display incorrectly. | 9 | Percentage of course (#16) · Issues · Group6 / Online-Learning · GitLab | Closed | DungNTK | 15/02/2023 | 18/02/2023 | 2 | home | course
| Login as new user. Join a course, after finished it, home page did not change status "free" to "Continue learning" and percentage of finished. | 10 |  | Closed | DucNT | 2023-10-03
| "Continue Learning" button is not working (error 404) | 11 | Course part (#17) · Issues · Group6 / Online-Learning · GitLab | Doing | DungNTK | 15/02/2023 | 18/02/2023 | 2 | user | course
Missing function of old version? | Where are "Forget password", "Change Password" function ???? | 12 | Missing function (#11) · Issues · Group6 / Online-Learning · GitLab | Closed | KienPT | 2023-03-02 | 2023-05-02 | 1 | user | search
Home / Login | Login if failed page direct to another home page? | 13 | Login fail lead to another home page (#12) · Issues · Group6 / Online-Learning · GitLab | Closed | KienPT | 2023-07-02 | 2023-08-02 | 1 | user | home/ login
| Validate username and password | 14 |  | Closed | VinhTD | 2023-10-03
| Login successful only if account has been already created and information is saved in database | 15 |  | Closed | DungNTK | 2023-10-03
| Login with facebook and google account is not working. | 16 | Login with gmail/facebool/git (#14) · Issues · Group6 / Online-Learning · GitLab | Done | KhangTD | 2023-07-02 | 2023-08-02 | 1 | user | login
| Username and password must be stored in database fisrt, if it not exist in database then that user is not exist and should be register. | 17 |  | Done | DucNT | 2023-06-02
Register | Validate username, password and confirm password in register | 18 |  | Done | VinhTD | 2023-08-02
| Password and password to confirm must be exactly the same | 19 |  | Done | VinhTD | 2023-08-02
| After username and password are validated, save information in database to call later. | 20 |  | Done | VinhTD | 2023-06-02
Comments | Comment of course cannot load to page | 21 | Comments cannot load (#13) · Issues · Group6 / Online-Learning · GitLab | Done | KienPT | 2023-08-02 | 2023-10-02 | 1 | user | comment
| User must be logged in to post a coment or reply to another comment | 22 |  | Done | KhangTD | 2023-04-03
| After submit reply or comment, information of the comment will be insert into database to store. | 23 |  | Done | KhangTD | 2023-04-03
Course screen | They did not have database for "Method" chapter | 24 | Chapter database (#18) · Issues · Group6 / Online-Learning · GitLab | Done | DucNT | 15/02/2023 | 17/02/2023 | 2 | database | course
| Click finish on Git lesson it will redirect to lesson of Java course. (Example: click finish lesson 1 of Git course will direct to lesson 1 of Java course). | 25 | Finish button in lesson (#19) · Issues · Group6 / Online-Learning · GitLab | Done | KhangTD | 20/02/2023 | 21/02/2023 | 2 | user | finish button
| As same issue as Git cousrse with "Finish" button | 26 | Finish button in lesson (#19) · Issues · Group6 / Online-Learning · GitLab | Done | KhangTD | 20/02/2023 | 21/02/2023 | 2 | user | finish button
| Time needed to finish course should display and | 27 |  | Closed | DungNTK | 2023-06-02
| Course detail need to be clear, so as goal for each course | 28 |  | Closed | DungNTK | 2023-06-02
| Details of course will be display fully when user enter a course | 29 |  | Closed | DucNT | 2023-08-02
Quizz | User must be logged in to take quiz | 30 |  | Done | KienPT | 21/02/2023
| Did not have database for quiz yet | 31 | Database for Question (#20) · Issues · Group6 / Online-Learning · GitLab | Done | DucNT | 19/02/2023 | 21/02/2023 | 2 | database | quiz
| Question should be random chosen in database | 32 |  | Done | VinhTD | 21/02/2023
| The content of the question should be in the lesson content | 33 |  | Done | VinhTD | 21/02/2023
| Only 1 choice can be selected, select the second choice will deselect the first choice | 34 |  | Done | VinhTD | 20/02/2023
| User can review question after submit, mark, status, time will be displayed | 35 |  | Done | KienPT | 2023-04-03
| Submit button direct page to homepage | 36 |  | Closed | DungNTK | 22/2/2023
| After submit quiz, data of the quiz have just taken will be stored in database to call later. | 37 |  | Done | KhangTD | 20/02/2023
|  | 38 | Status for new user when join a course (#21) · Issues · Group6 / Online-Learning · GitLab | Closed | KhangTD | 17/02/2023 | 21/02/2023 | 2 | user | home
Front end | Some part like header and course at the middle is need to fix for better visual | 39 | HTML/CSS (#23) · Issues · Group6 / Online-Learning · GitLab | Closed | KienPT | 24/02/2023 | 28/02/2023 | 2 | home | home
| Coloring, settings, motions must be acceptable | 40 |  | Done | KienPT | 22/2/2023
| Font, text should be in the right size, position for better visual of website | 41 |  | Done | DucNT | 22/2/2023
| Text of Course is bad, need to enhance | 42 |  | Done | DucNT | 22/2/2023
| Color is bad, need some enhancement | 43 |  | Done | KienPT | 22/2/2023
Search | Search function is not working. No servlet (error 404) | 44 | Search (#24) · Issues · Group6 / Online-Learning · GitLab | Open | VinhTD | 28/02/2023 | 2023-03-03 | 3 | search | search
| Button search is broken. Must press 'enter' to search. | 45 | Search (#24) · Issues · Group6 / Online-Learning · GitLab | Open | VinhTD | 28/02/2023 | 2023-03-03 | 3 | search | search
| User can search for course, lesson, ... not login required | 46 |  | Closed | KhangTD | 2023-01-03
| Search submitted will return a result contains what user search for. | 47 |  | Closed | KienPT | 2023-04-03
| If can not found what user searching for, page should have an anouncement like "Can not find <word> " | 48 |  | Closed | KienPT | 20/02/2023
Lesson | When click on "Finish" button at the end of the page, the menu of lesson at the head is dissappear. | 49 |  | Open | DungNTK | 28/02/2023 | 2023-03-03 | 3 | lesson | course
| Lesson detail can be view only when user logged in | 50 |  | Closed | DungNTK | 2023-01-03
| After finish each lesson, need to save that progress for the next time user enter the page they can continue their learning. If not press the "Finish" button, that lesson cannot be finished and the progress will not be saved | 51 |  | Closed | DungNTK | 28/02/2023
| Edit lesson not working properly | 53 |  | Closed | VinhTD | 2023-01-03
| Add new lesson not working properply | 54 |  | Closed | DucNT | 28/02/2023
Course | Course detail can be view even user have not log in | 55 |  | Closed | KhangTD | 2023-01-03
| Each course should contain description, number of lesson of course, rate, number of user have enrolled, estimation of time to finish the course | 56 |  | Done | DucNT | 2023-02-03
| Add new course not working properply | 57 |  | Closed | DungNTK | 2023-02-03
Write code to do | Write detail code function, jsp, html, css for Profile of user | 54 | Profile (#25) · Issues · Group6 / Online-Learning · GitLab | Open | DungNTK | 28/02/2023 | 2023-06-03 | 3 | profile | user
| Write detail code function, jsp, html, css for Information of user | 55 | Information (#26) · Issues · Group6 / Online-Learning · GitLab | Open | VinhTD | 28/02/2023 | 2023-06-03 | 3 | information | user
| Write code for Notification | 56 |  | Closed | KienPT | 28/2/2023