## Project
Online-learning Project Tracking
# | Screen/Function | Feature | Actor | Screen/Function Description | In Charge | Status | Actual | Updated | Update Details
1 | Home page | Display | User | Provide information about your website, including its introduction, purpose, topics and content provided on the website. | KiênPT | Updated | iter1 | iter3 | update more template to beautifull home page
2 | Register | Common | User | Provide a screen which have sumbit input to user register an account for website | KhangTD | Done | iter1 | none
3 | Course Detail | Common | User | This page should list the available course words, including the course word name, description, price, and duration of the course word. | KhangTD | Done | iter1 | iter2
4 | Chapter Detail | Common | User | This page provides learning materials for courses. Materials may include videos, lectures, exercises, and tests | Dungntk + DucNT | Done | iter2 | iter3 | update information about description of lesson, video, image. Fix bug in header menu.
5 | User Login | Common | User | This is a pop-up screen which allows the user to enter email & password to login; on this page, there are also links for user to register new information or reset the password for the case s/he forget it | KhangTD | Done | iter1 | none
5 | Forgot Password | Common | User | The screen that allows user to retrieve password when forgotten | KhangTD | Done | iter1 | none
6 | Change Password | Common | User | The screen that allows the user to change the account's password | KhangTD | Done | iter1 | none
7 | Question Library and Lesson Library | Storage | Admin | Store question information as well as lessons into the group's database. | DucNT | Updated | iter1 | iter2 | Update more question into database and add more lessondetail
8 | Practice | Common | User | The test page contains all the questions in the web's question library, to help students check what they have learned in the web. At the same time, it helps to assess the ability of students studying in the website. | VinhTD +KienPT | Done | iter2 | iter3
9 | View mark report | Common | User | This function will help student view the mark after they finished the multiple choice exam. | VinhTD +KienPT | Done | iter2 | iter3
10 | View wrong answer | Common | User | This function will help student view the correct and wrong answer when they finished exam and viewed mark. | VinhTD +KienPT | Done | iter2 | ier3
11 | Profile | Common | User | Profile page will provide users with Profile Picture, Full Name, Gender, Date of Birth, Date of Birth, Email Address, Description of Yourself,... | KhangTD | Doing | iter2 | iter3
12 | Statistical chart | Display | Admin | Statistical charts can show how engaged users are with the website, Course completion rates. Visualizing feedback received from users, such as ratings and reviews. Statistical charts can provide insights into sales and revenue | KhangTD | To Do | iter3 | iter4
13 | Discussion | Common | User | The Comment author must fill out name, Users must be registered and logged in to comment, Enable threaded (nested) comments, Comments displayed with the comments at the top for each page. | KienPT | Done | Iter2 | none
14 | Lesson detail | Display | Admin | List out all information contained in each course that has been researched and synthesized from reliable sources and has been used by major universities in the curriculum. | Dungntk + DucNT | Done | iter1 | iter2
15 | Lesson function | common | User | Those function were created to serve student easily study with functions such as marking the lesson completed as well as a menu of lessons included in the chapter appearing above the lesson | Dungntk | Done | iter2 | iter3
16 | Purchase course | Common | Student | A paid course is usually designed and developed to ensure higher teaching quality. It provides learners with high-quality study materials, in-depth lectures, and support from highly specialized instructors. | DucNT | Done | iter3 | none
17 | Video for purchase course | Common | Student | A video is recorded by the instructor under each lesson to teach in-depth knowledge of the lesson. | DucNT | Doing | iter3 | none
18 | Change Avatar | Common | User | Update an avatar so that you can be recognized in the comments of the lock and beautify your feature. | KienPT | To Do | iter3 | iter4
19 | Change profile information | Common | User | Update an information of user in profile such as user name, user phone, user address, user email… | KhangTD | Doing | iter3 | iter4
20 | Search course | Common | User | A search bar included to help users quickly find specific content on the website | VinhTD | To Do | iter3 | none
21 | Manager User | Private | Admin | This page should list the available user of website. Admin has a permission to change the information of user. | KienPT | Doing | iter4 | none
22 | Manager Course | Private | Admin | This page should list the available course of website. Admin have a permission to change the information of course. | KienPT | Doing | iter4 | none

## Iter1
Iteration Tracking - Iteration 1
# | Screen/function | Feature | Screen/Function Description | In charge | Status | SRS | SDS | Note
1 | Home page | display | The features of a home page have display the logo and branding of the website, a navigation bar that allows users to quickly access different sections of the website, Home pages may include calls-to-action, such as buttons or links, that encourage users to take a specific action, such as signing up for a newsletter or making a purchase. | KiênPT | Doing | II.1 | II.3
2 | Question Library and Lesson Library | storage | Store question information as well as lessons into the group's database. | ĐứcNT | Doing | none | none
3 | User Login | Common | 'This is a pop-up screen which allows the user to enter email & password to login; on this page, there are also links for user to register new information or reset the password for the case s/he forget it | KhangTD | Done | II.2 | II.2
4 | Forgot Password | Common | The screen that allows user to retrieve password when forgotten | KhangTD | Done
5 | Change Password | Common | The screen that allows the user to change the account's password | KhangTD | Done | II.6 | II.4
6 | Lesson detail | Common | List out all information contained in each course that has been researched and synthesized from reliable sources and has been used by major universities in the curriculum. | Dungntk + DucNT | Done | II.12 | II.6
7 | Course Detail | Common | This page should list the available course words, including the course word name, description, price, and duration of the course word. | Dungntk | Done | II.4 | II.5
8 | Register | Common | Provide a screen which have sumbit input to user register an account for website | KhangTD | Done | II.1 | II.1

## Iter2
Iteration Tracking - Iteration 2
Information in the columns A-F must be provided as the planned scope for the iteration
Columns B-D are copied from the sheet Product
Columns E-J are updated/filled by the end of the iteration
# | Screen / Function | Feature | Screen/Function Description | In Charge | Status | SRS | SDS | Notes
1 | Chapter Detail | Common | This page provides learning materials for courses. Materials may include videos, lectures, exercises, and tests | Dungntk | Done | II.5 | II.5
2 | Practice | Student | The test page contains all the questions in the web's question library, to help students check what they have learned in the web. At the same time, it helps to assess the ability of students studying in the website. | VinhTD +KienPT | Doing | II.7 | II.9
3 | View mark report | Student | This function will help student view the mark after they finished the multiple choice exam. | VinhTD +KienPT | Doing | II.8 | II.10
4 | View wrong answer | Student | This function will help student view the correct and wrong answer when they finished exam and viewed mark. | VinhTD +KienPT | Doing | II.9 | II.11
5 | Profile | User | Profile page will provide users with Profile Picture, Full Name, Gender, Date of Birth, Date of Birth, Email Address, Description of Yourself,... | KhangTD | Doing | II.10 | II.13
6 | Discussion | Common | The Comment author must fill out name, Users must be registered and logged in to comment, Enable threaded (nested) comments, Comments displayed with the comments at the top for each page. | VinhPT | Doing | II.11 | II.12
7 | Lesson function | Common | Those function were created to serve student easily study with functions such as marking the lesson completed as well as a menu of lessons included in the chapter appearing above the lesson | Dungntk | Doing | II.12 | II.6
Note on G5: KienNT: The name of section in the SRS (software requirement specification) document
Note on H5: KienNT: The name of section in the SDS (software design specification) document

## Iter3
Iteration Tracking - Iteration 3
# | Screen / Function | Feature | Screen/Function Description | In Charge | Status | SRS | SDS | Notes
1 | Statistical chart | User | Statistical charts can show how engaged users are with the website, Course completion rates. Visualizing feedback received from users, such as ratings and reviews. Statistical charts can provide insights into sales and revenue | KhangTD | To Do | II.16
2 | Change profile information | User | Update an information of user in profile such as user name, user phone, user address, user email… | KhangTD | Doing | II.16
3 | Update avatar | User | Update an avatar so that you can be recognized in the comments of the lock and beautify your feature. | KienPT | To Do | II.15
4 | Purchase course | Student | A paid course is usually designed and developed to ensure higher teaching quality. It provides learners with high-quality study materials, in-depth lectures, and support from highly specialized instructors. | DucNT | Doing | II.13
5 | Video for purchase course | Student | A video is recorded by the instructor under each lesson to teach in-depth knowledge of the lesson. | DucNT | Doing | II.14
6 | Search course | user | A search bar included to help users quickly find specific content on the website | KienPT | Doing |  | II.14
Note on G3: KienNT: The name of section in the SRS (software requirement specification) document
Note on H3: KienNT: The name of section in the SDS (software design specification) document

## Iter4
Iteration Tracking - Iteration 4
# | Screen / Function | Feature | Screen/Function Description | In Charge | Status | SRS | SDS | Notes
1 | Manager User | Private | This page should list the available user of website. Admin has a permission to change the information of user. | KienPT | Doing | II.20
2 | Manager Course | Private | This page should list the available course of website. Admin have a permission to change the information of course. | KienPT | Doing | II.19
Note on G5: KienNT: The name of section in the SRS (software requirement specification) document
Note on H5: KienNT: The name of section in the SDS (software design specification) document