## Issues Report
Title | Description | Issue ID | URL | State | Assignee | Created At | Due Date | Milestone | Labels | Functions/Screens
Home screen | Link in the footer part is not working | 1 | Home screen (#10) · Issues · Group6 / Online-Learning · GitLab | Closed | DucNT | 2023-01-02 | 2023-03-02 | 1 | home | home
Missing function of old version? | Where are "Forget password", "Change Password" function ???? | 2 | Missing function (#11) · Issues · Group6 / Online-Learning · GitLab | Closed | KienPT | 2023-03-02 | 2023-05-02 | 1 | user | search
Home / Login | Login if failed page direct to another home page? | 3 | Login fail lead to another home page (#12) · Issues · Group6 / Online-Learning · GitLab | Closed | KienPT | 2023-07-02 | 2023-08-02 | 1 | user | home/ login
Login | Login with facebook and google account is not working. | 4 | Login with gmail/facebool/git (#14) · Issues · Group6 / Online-Learning · GitLab | Done | KhangTD | 2023-07-02 | 2023-08-02 | 1 | user | login
Comments | Comment of course cannot load to jsp page | 5 | Comments cannot load (#13) · Issues · Group6 / Online-Learning · GitLab | Done | KienPT | 2023-08-02 | 2023-10-02 | 1 | user | comment
Home screen | Link in header part is not attached yet. Only "Learning" button is return to index page. | 7 | Header links (#15) · Issues · Group6 / Online-Learning · GitLab | Closed | KhangTD | 2023-10-02 | 2023-12-02 | 2 | home | home
Home screen (logged in) / Course Part | Percentage of finished lessons in course is display incorrectly. | 8 | Percentage of course (#16) · Issues · Group6 / Online-Learning · GitLab | Closed | DungNTK | 15/02/2023 | 18/02/2023 | 2 | home | course
Home screen (logged in) / Course Part | "Continue Learning" button is not working (error 404) | 9 | Course part (#17) · Issues · Group6 / Online-Learning · GitLab | Doing | DungNTK | 15/02/2023 | 18/02/2023 | 2 | user | course
Course screen/ Java | They did not have database for "Method" chapter | 10 | Chapter database (#18) · Issues · Group6 / Online-Learning · GitLab | Done | DucNT | 15/02/2023 | 17/02/2023 | 2 | database | course
Course/ Git | Click finish on Git lesson it will redirect to lesson of Java course. (Example: click finish lesson 1 of Git course will direct to lesson 1 of Java course). | 12 | Finish button in lesson (#19) · Issues · Group6 / Online-Learning · GitLab | Done | KhangTD | 20/02/2023 | 21/02/2023 | 2 | user | finish button
Course/ SQL | As same issue as Git cousrse with "Finish" button | 13 | Finish button in lesson (#19) · Issues · Group6 / Online-Learning · GitLab | Done | KhangTD | 20/02/2023 | 21/02/2023 | 2 | user | finish button
Quizz | Did not have database for quiz yet | 14 | Database for Question (#20) · Issues · Group6 / Online-Learning · GitLab | Done | DucNT | 19/02/2023 | 21/02/2023 | 2 | database | quiz
New account on home screen | Login as new user. Join a course, after finished it, home page did not change status "free" to "Continue learning" and percentage of finished. | 15 | Status for new user when join a course (#21) · Issues · Group6 / Online-Learning · GitLab | Closed | KhangTD | 17/02/2023 | 21/02/2023 | 2 | user | home
Home | Logo is haven't been changed yet | 16 | Logo page is missing (#22) · Issues · Group6 / Online-Learning · GitLab | Done | VinhTD | 20/02/2023 | 29/02/2023 | 2 | home | login
Front end | Some part like header and course at the middle is need to fix for better visual | 17 | HTML/CSS (#23) · Issues · Group6 / Online-Learning · GitLab | Closed | KienPT | 24/02/2023 | 28/02/2023 | 2 | home | home
Search | Search function is not working. No servlet (error 404) | 18 | Search (#24) · Issues · Group6 / Online-Learning · GitLab | Open | VinhTD | 28/02/2023 | 2023-03-03 | 3 | search | search
Search button | Button search is broken. Must press 'enter' to search. | 19 | Search (#24) · Issues · Group6 / Online-Learning · GitLab | Open | VinhTD | 28/02/2023 | 2023-03-03 | 3 | search | search
Lesson screen | When click on "Finish" button at the end of the page, the menu of lesson at the head is dissappear. | 20 |  | Open | DungNTK | 28/02/2023 | 2023-03-03 | 3 | lesson | course
Write code for Profile | Write detail code function, jsp, html, css for Profile of user | 21 | Profile (#25) · Issues · Group6 / Online-Learning · GitLab | Open | DungNTK | 28/02/2023 | 2023-06-03 | 3 | profile | user
Write code for Information | Write detail code function, jsp, html, css for Information of user | 22 | Information (#26) · Issues · Group6 / Online-Learning · GitLab | Open | VinhTD | 28/02/2023 | 2023-06-03 | 3 | information | user